## Material Costing
Actuation System | Cost / pc | Qty Req | Total Cost
Clamps | 10000 | 2 | 20000
Clamp Mounts | 10000 | 2 | 20000
Load Cell | 177000 | 1 | 177000
Load Cell Mount | 10000 | 1 | 10000
Linear Actuator | 35000 | 1 | 35000
Limit Switches | 2000 | 2 | 4000
Limit Switch Mount | 2000 | 2 | 4000
Device Supports | 1000 | 2 | 2000
Frame | 100000 | 1 | 100000
MCU | 30000 | 2 | 60000
PCB | 25000 | 1 | 25000
Motor Drive | 5000 | 1 | 5000
Power Supply | 10000 | 1 | 10000
Buttons (Push Buttons) | 1000 | 5 | 5000
Buttons (Power Buttons) | 5000 | 2 | 10000
Emergency Stop Button | 4000 | 1 | 4000
Wiring | 5000 | 1 | 5000
Connectors | 5000 | 1 | 5000
Internal Mountings | 10000 | 1 | 10000
LED Lights | 3000 | 1 | 3000
0
Mock Arterial System |  |  | 0
Arterial Plate (Acrylic) | 50000 | 1 | 50000
0
0
Heated Water Bath |  |  | 0
Water Tank | 50000 | 1 | 50000
Mounting Platform Arterial System | 5000 | 1 | 5000
Heaters | 10000 | 2 | 20000
Temperature Sensor | 1000 | 2 | 2000
Temp. Regulator | 5000 | 1 | 5000
0
Camera System |  |  | 0
HD Camera | 50000 | 1 | 50000
Camera Mount | 5000 | 1 | 5000 | usd
|  | Total (PKR) | 701000 | 2521.5827
3530.2158
|  |  | Misc | 520
|  |  | Final Total | 4050.2158 | usd

## Timeline
S. # | Activity | W-1 | W-2 | W-3 | W-4 | W-5 | W-6 | W-7 | W-8 | W-9 | W-10 | W-11 | W-12 | W-13
1 | Planning | bar: W-1
2 | Procurement | bar: W-1 to W-6
3 | Design: Schematic | bar: W-2
4 | Design: Software | bar: W-2
5 | Design: Mechanical | bar: W-2 to W-3
6 | Development: Electronics | bar: W-4 to W-8
7 | Development: Software | bar: W-4 to W-9
8 | Fabrication: Actuation System | bar: W-3 to W-6
9 | Fabrication: Mock Arterial System | bar: W-4 to W-5
10 | Fabrication: Visual System | bar: W-7
11 | Fabrication: Water Bath | bar: W-6 to W-7
12 | Fabrication: Control System Casing | bar: W-6; W-9
13 | Integration | bar: W-7 to W-11
14 | Optimisation | bar: W-10 to W-12
15 | Testing | bar: W-12 to W-13
16 | Dispatch

## Tasks
S # | Activity | SSA # | Sub-Activity | HR | Time (hrs) | Remarks
1 | Design: Schematic | 1.1 | Actuation System
|  | 1.2 | Load Sensing System
|  | 1.3 | Water Heating System
|  | 1.4 | Visual System
2 | Design: Software | 2.1 | User Interface
|  | 2.2 | Control System
3 | Design: Mechanical | 3.1 | Actuation System | Haris Ali | 16
|  | 3.2 | Load Cell Mounting | Haris Ali | 3
|  | 3.3 | Mock Arterial Plate | Haris Ali | 12
|  | 3.4 | Water Heating Bath | Haris Ali | 3
|  | 3.5 | Camera Mounting | Haris Ali | 2
|  | 3.6 | Control Hardware Mountings | Haris Ali | 4
4 | Development Electronics | 4.1 | Microcontroller Setup
|  | 4.2 | Motor Integration
|  | 4.3 | Load Cell Integration
|  | 4.4 | Load Cell Calibration
|  | 4.5 | Pneumatic Clamping System Integration
|  | 4.6 | PC Communication
|  | 4.7 | Buck Converter Integration
|  | 4.8 | PCB Development
|  | 4.9 | Temperature Regulation System Integration
5 | Development: Software | 5.1 | Front End Development
|  | 5.2 | MCU Communication Establishment
|  | 5.3 | Graph Panels
|  | 5.4 | Control Button Implementation
|  | 5.5 | Camera Interfacing
|  | 5.6 | File Handling
|  | 5.7 | User Login System
6 | Fabrication: Actuation System | 6.1 | Mounting for Linear Actuator | Intern # 3 | 56
|  | 6.2 | Mounting for Pneumatic Clamp | Intern # 3 | 32
|  | 6.3 | Mounting for Load Cell | Intern # 3 | 24
|  | 6.4 | Device Support | Usama | 16
7 | Fabrication: Mock Arterial System | 7.1 | Mock Arterial Plate | Usama
|  | 7.2 | Plate Mounting | Usama
8 | Fabrication: Visual System | 8.1 | Camera Mounting | Intern # 3
|  | 8.2 | Camera Housing | Intern # 3
9 | Fabrication: Water Heating Bath | 9.1 | Water Tank | Usama | 56
|  | 9.2 | Heater Mounting | Usama | 8
|  | 9.3 | Temperature Regulator Mounting | Usama | 10
|  | 9.4 | Temperature Sensor Mounting | Usama | 8
10 | Fabrication: Control System Casing | 10.1 | Mounting for Electronic Hardware | Intern # 3
|  | 10.2 | Casing Frame | Intern # 3
|  | 10.3 | Frame Cladding | Intern # 3
11 | Integration | 11.1 | Mechanical Assembly | Usama
|  | 11.2 | Electronic Assembly
|  | 11.3 | Software Integration
12 | Optimisation | 12.1 | Modular Testing
|  | 12.2 | Electronics Optimisation
|  | 12.3 | Software Optimisation
|  | 12.4 | Mechanical Optimisation
13 | Testing | 13.1 | Functional Testing
|  | 13.2 | Safety Testing
|  | 13.3 | Fatigue Testing

## HR
Monthly
S. # | Name | Work Hours | Salary | Cost / Hr | Total Cost (PKR)
1 | Haris | 60 | 270000 | 1687.5 | 101250
2 | Ammad | 52 | 270000 | 1687.5 | 87750
3 | Ibraheem | 162 | 180000 | 1125 | 182250
4 | Usama | 260 | 40000 | 250 | 65000
5 | Intern # 1 (Embedded) | 520 | 40000 | 250 | 130000
6 | Intern # 2 (Software) | 520 | 25000 | 156.25 | 81250
7 | Intern # 3 (Embedded) | 520 | 25000 | 156.25 | 81250
8 | Intern # 4 (Fabrication) | 520 | 25000 | 156.25 | 81250
|  |  | Grand Total (PKR) |  | 810000
|  |  | Grand Total (USD) |  | 2913.6691

## Summary
Expense Head | Amount (USD)
Material | 4050.2158
Human Resource | 2913.6691
FOH | 1392.777
Markup | 2089.1655
Total (USD) | 10445.8273